## CC
This project planning template was developped for
The Crossborder Journalism Campus
https://crossborderjournalismcampus.eu/
A cross-border collaborative journalism education project
The template is free to use under creative commons BY NC SA
Tthe templates are intended as inspiration for discussion in journalism education and training

## To-do & timeline
This is a so-called gantt-chart: A to-do list combined with a timeline. Each task in the to-do list can be broken down to numerous sub-tasks, team members can take the tasks upon them, and for each task an expected workload can be estimated. You can also make the timeline more detailed than months. Based upon that, a budget with number of work days and team meetings can be prepared. Use it to discuss with your team, adapt it to your start and end dates, your work tasks - and you'll have an overview tool to revisit and revise during the research process.
TASK / MONTH | October | November | December | January | February | March | April | May | June | July | August | September | October
JOURNALISM Background reading
JOURNALISM Documnet aquisition, FOI requests
JOURNALISM Data aquisition
JOURNALISM Mapping experts and actors (academic experts, interest organisations, civil society, business, policy makers)
JOURNALISM Background interviews (academic experts, interest organisations, civil society)
JOURNALISM Document & data preparation and analysis
JOURNALISM Interviews
EDITORIAL COORDINATION Setting up the team, meetings
EDITORIAL COORDINATION Securing funding
EDITORIAL COORDINATION Secure digital work space
EDITORIAL COORDINATION Regular editorial meetings
PUBLICATION Status check with experts
PUBLICATION Writing
PUBLICATION fact check
PUBLICATION - - - the big moment!
PUBLICATION follow up (including to reunite and follow up a year later if relevant)

## Budget
For the budget, make sure you have covered as many costs as you can predict. It is wise to group costs such as team costs (working time) and expenses. Again - this is only a template, use it for inspiration and adapt to precisely your project. See comments in the fields for further remarks.
OUT | [6 empty] | IN
Team members | [6 empty] | Income
# | Name, surname | Daily/weekly/monthly income/honorary in € | Number of days/weeks or months |  | Total cost € | Remarks | Source | applied | secured | Total € | Remarks
1 | [6 empty] | Publication
2 | [6 empty] | Work grant
3 | [6 empty] | Journalism award with money
4
[5 empty] | 0 |  |  |  |  | 0
Expenses
# | Expenses | Amount in local currency | Currency | Exchange Rate | Amount in € | Remarks
1 | Team meeting
2 | Secure digital work space
3 | Travel to interviews
4 | FOI and data related costs
0
Total
[5 empty] | Amount in € | Remarks
0
Note on C5: [Trådet kommentar] Din version af Excel lader dig læse denne trådede kommentar. Eventuelle ændringer vil dog blive fjernet, hvis filen åbnes i en nyere version af Excel. Få mere at vide: https://go.microsoft.com/fwlink/?linkid=870924 Kommentar: Discuss in the team: Is this a team of freelancers and/or staffers, and how much funding is needed to secure the production? Should income levels be the same across the team or be adapted to the national expected costs? Besvar: Also, decide for your budget whether you want to count in days, weeks or months. For shorter projects or smaller taks and subtasks, daily makes sense, for longer projects weekly or even monthly is easier.
Note on D5: [Trådet kommentar] Din version af Excel lader dig læse denne trådede kommentar. Eventuelle ændringer vil dog blive fjernet, hvis filen åbnes i en nyere version af Excel. Få mere at vide: https://go.microsoft.com/fwlink/?linkid=870924 Kommentar: Are you time optimists or realists ie are you usually underestimating the time necessary for a given task or are you realistic?
Note on J7: [Trådet kommentar] Din version af Excel lader dig læse denne trådede kommentar. Eventuelle ændringer vil dog blive fjernet, hvis filen åbnes i en nyere version af Excel. Få mere at vide: https://go.microsoft.com/fwlink/?linkid=870924 Kommentar: If you apply for multiple grants, do mention this here with a remark on timeline of the applied grant. Funders are familiar with multiple grant givers and multiple timelines as a working condition.
Note on L10: [Trådet kommentar] Din version af Excel lader dig læse denne trådede kommentar. Eventuelle ændringer vil dog blive fjernet, hvis filen åbnes i en nyere version af Excel. Få mere at vide: https://go.microsoft.com/fwlink/?linkid=870924 Kommentar: This should match the total cost field in order to make the work plan realistic. Funding may, however, only be secured while the work process already is in motion - discuss in the team how feasible this is.
Note on B13: [Trådet kommentar] Din version af Excel lader dig læse denne trådede kommentar. Eventuelle ændringer vil dog blive fjernet, hvis filen åbnes i en nyere version af Excel. Få mere at vide: https://go.microsoft.com/fwlink/?linkid=870924 Kommentar: Agree which costs the team covers.